## Downtime Tracker
Date | Issue | Effect | Discovered_by | Reported to | Attributable Cause | Status | Downtime (Resolution Time) | Permanent Resolution | Month
2022-12-14 | UI/UX Issues | Access Issues | Victor | Mark - Physical Demo/Illustration | Technical Issues | Resolved | 48 | One-time fix | December
2022-12-14 | Notification Issues | Access Issues | Trizah | Mark - Phone | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | December
2023-01-17 | All systems down | Access Issues | Joan | Mark - Phone, then Kaki | Technical Issues | Resolved | 12 | Currently Unclear | January
2023-05-03 | App Accessibility | Access Issues | Victor | Safaricom Team, Ezekiel | External Factors | Resolved | 264 | External Control | May
2023-05-08 | App Accessibility | Access Issues | Victor | Safaricom Team (MbaraK) | Maintainance | Resolved | 456 | User Experience Overhauled | May
2023-06-06 | Checkout and Payment Issues | Transaction Issues | Victor | Mark - Physical Demo & Video | Unclear | Resolved | 48 | Fixed | June
2023-06-06 | Quote and Benefits Issues | Transaction Issues | Victor | Mark - Physical Demo & Screenshot | Technical Issues | Resolved | 24 | Fixed | June
2023-06-13 | Checkout and Payment Issues | Information and Rate Issues | Rebekah | Mark - Physical Demo | Technical Issues | Resolved | 48 | Pending | June
2023-06-13 | Checkout and Payment Issues | Transaction Issues | Victor | Mark - Physical Demo & Screenshots | Technical Issues | Resolved | 12 | Fixed | June
2023-06-14 | Quote and Benefits Issues | Information and Rate Issues | Rebekah | Mark - Demo Video | Technical Issues | Resolved | 24 | Fixed | June
2023-06-14 | Quote and Benefits Issues | Information and Rate Issues | Victor | Mark - Shared Screenshots | Technical Issues | Resolved | 24 | Fixed | June
2023-06-15 | Data Display Issues | User Experience Issues | Ezekiel | Mark - Shared Screenshot | Unclear/Undisclosed | Unresolved | 48 | Undetermined | June
2023-06-22 | Data Display Issues | User Experience Issues | Ezekiel | Mark - Shared screenshots | Unclear/Undisclosed | Resolved | 24 | Currently Unclear | June
2023-06-22 | UI/UX Issues | Information and Rate Issues | Victor | Mark - Shared Screenshots | Unconcluded | Unresolved | 12 | Currently Unclear | June
2023-06-26 | UI/UX Issues | User Experience Issues | Joseph (Intern) | Mark - Shared Screenshots | Unconcluded | Unresolved | 12 | Currently Unclear | June
2023-06-28 | UI/UX Issues | User Experience Issues | Joseph (Intern) | Mark - Shared Screenshot | Unclear/Undisclosed | Unresolved | 48 | Currently Unclear | June
2023-06-29 | Quote and Benefits Issues | Access Issues | Victor | Mark - Physical Demo | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | June
2024-07-06 | Quote and Benefits Issues | User Experience Issues | Victor | Mark - Shared Screenshot | Configuration Errors | Resolved | 48 | Currently Unclear | July
2024-08-18 | Quote and Benefits Issues | User Experience Issues | Victor | Mark - Shared Screenshot | Unclear/Undisclosed | Resolved | 24 | Currently Unclear | August
2024-08-22 | Kenbright.co.ke Is Down | Unknown | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | August
2024-08-30 | UI/UX Issues | User Experience Issues | Ezekiel | Mark - via Chat | Unclear/Undisclosed | Resolved | 48 | Currently Unclear | August
2024-08-30 | UI/UX Issues | User Experience Issues | Ezekiel | Mark - via Chat | Configuration Errors | Resolved | 48 | Currently Unclear | August
2024-09-14 | UI/UX Issues | User Experience Issues | Ezekiel | Mark - via Chat | Configuration Errors | Resolved | 24 | Currently Unclear | September
2024-09-14 | Data Display Issues | User Experience Issues | Ezekiel | Mark - via Chat | Unclear/Undisclosed | Resolved | 24 | Currently Unclear | September
2024-09-28 | Notification Issues | Access Issues | Patricia | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | September
2024-09-28 | Infrastructure Issues | Access Issues | Mark | Escalated to Kaki | External Factors | Resolved | 12 | Currently Unclear | September
2024-01-18 | Vehicle.co.ke Down | Access Issues | Victor | Mark - via Chat | External Factors | Resolved | 12 | Currently Unclear | January
2024-01-21 | Quote and Benefits Issues | Information and Rate Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | January
2024-02-01 | Quote and Benefits Issues | User Experience Issues | Victor | Mark - via Chat | Configuration Errors | Resolved | 12 | Currently Unclear | February
2024-02-08 | Data Display Issues | User Experience Issues | Patricia | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | February
2024-02-14 | Quote and Benefits Issues | Access Issues | Gilbert | Mark - via Chat | Unclear/Undisclosed | Resolved | 48 | Currently Unclear | February
2024-03-03 | App Accessibility | Access Issues | Victor | Mark - via Chat | Technical Issues | Resolved | 12 | Currently Unclear | March
2024-03-05 | App Accessibility | Access Issues | Victor | Mark - via Chat | Technical Issues | Resolved | 12 | Currently Unclear | March
2024-03-06 | App Accessibility | Access Issues | Victor | Mark - via Chat | Technical Issues | Resolved | 12 | Currently Unclear | March
2024-03-10 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-03-14 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-03-16 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-03-18 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-03-21 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-03-26 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | March
2024-04-17 | Quote and Benefits Issues | User Experience Issues | Victor | Mark - Shared Screenshot | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | April
2024-04-22 | Notification Issues | Access Issues | Patricia | Mark - via Chat | Unclear/Undisclosed | Resolved | 48 | Currently Unclear | April
2024-04-29 | Notification Issues | Access Issues | Patricia | Mark - via Chat | Unclear/Undisclosed | Resolved | 24 | Currently Unclear | April
2024-04-30 | Quote and Benefits Issues | User Experience Issues | Victor | Mark - Shared Screenshot | Unclear/Undisclosed | Resolved | 48 | Currently Unclear | April
2024-05-04 | Notification Issues | Access Issues | Victor | Mark - Shared Screenshot | Unclear/Undisclosed | Unresolved | 24 | Currently Unclear | May
2024-09-12 | App Accessibility | Access Issues | Victor | Mark - via Chat | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | September
2024-10-09 | Notification Issues | Access Issues | Victor & Patricia | Mark - via Chat | Unclear/Undisclosed | Resolved | 24 | Currently Unclear | October
2024-10-28 | Checkout and Payment Issues | User Experience Issues | Stella | Mark - Shared Screenshot | Unclear/Undisclosed | Resolved | 12 | Currently Unclear | October